## Mill Alley
Derelict Mill Alley · Assets | [6 empty] | Scheme · Oct 19, 2026 – Jan 31, 2027 (Wed/Thu off)
Kit A · Left mill | Size (cm) | Blockout | Model | UVs | Material | In UE5 | Week 1 · Pre-production
[7 empty] | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25
A01 Wall flat | 400 x 400, 200 x 400, 100 x 400 | [5 empty] | Build a reference board | Paint over the reference | Day off | Day off | Camera match in Blender | Lock metrics, naming and folders | Lighting and mood paintover + Review 1
A02 Pilaster | 60 x 400, 25 projection
A03 Blind arch recess with brick infill | 300 x 600 | [5 empty] | 2026-10-19: Week 2 · Greybox
A04 Upper window, round head, glazed | 300 x 400 | [5 empty] | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01
A05 Arched loading door surround | 300 x 400 | [5 empty] | Greybox ground and both building masses in UE5 at scale | Greybox the left facade with placeholder A01 to A09 at final dimensions | Day off | Day off | Greybox the right facade with B01 to B09, including the ledge and light well | Greybox skybridge, chimney, end building and loading door | Blockout lighting + Review 2
A06 Outer and inner corner | 50 x 400
A07 String course | 400 long | [5 empty] | 2026-10-26: Week 3 · Tiling materials
A08 Parapet with coping | 400 x 100 | [5 empty] | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08
A09 Base course / plinth | 400 x 60 | [5 empty] | Source CC0 base materials | Build custom mask node groups in Blender | Day off | Day off | Brick sets M01 to M04 | M05 to M10 | Build M_Master_Kit in UE5 + Review 3
Kit B · Right building | Size (cm) | Blockout | Model | UVs | Material | In UE5
Week 4 · Trim sheets and Family A
B01 Wall flat, painted | 400 x 380, 200 x 380, 100 x 380 | [5 empty] | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15
B02 Window bay (opening, sill, lintel) | 300 x 380 | [5 empty] | Model T01 stone and T02 metal trim strips in Blender | T03 timber trim sheet | Day off | Day off | Model A01, A02, A06, A09 with bevels and UVs | Model A03 blind arch with infill, A05 door surround, A07 string course, A08 parapet | Model A04 window + Review 4
B03 Steel window insert: intact, broken, gutted | 140 x 220
B04 Door bay with timber door | 300 x 380 | [5 empty] | 2026-11-09: Week 5 · Families B, C and D
B05 Projecting ledge / plinth | 400 x 50, 60 deep | [5 empty] | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22
B06 Light well: walls, steps, landing | 120 x 380, 200 drop | [5 empty] | Model B01, B07, B08, B09 | Model B02 window bay and the three B03 steel window variants | Day off | Day off | Model B04 door bay, B05 ledge, B06 light well | Model Family C | Model Family D ground pieces + Review 5
B07 Floor band | 400 long
B08 Outer corner | 50 x 380 | [5 empty] | 2026-11-16: Week 6 · Hero: skybridge (H1)
B09 Roof edge with gutter | 400 long | [5 empty] | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29
Kit C · Structure | Size (cm) | Blockout | Model | UVs | Material | In UE5 | Plan the skybridge from reference | Sculpt in Blender | Day off | Day off | Retopo the low poly, UV into two 4K sets | Bake in Marmoset | Finish texturing, import, place + Review 6
C01 Steel I-beam | 100, 200, 400 long, 30 deep | [5 empty] | 2026-11-23: Week 7 · Heroes H2, H3, H6, H7
C02 Drainpipe: straight, elbow, offset, shoe | 100, 200, 400; 10 diameter | [5 empty] | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06
C03 Hopper head | 30 x 30 | [5 empty] | Model the chimney and red end building | Texture the chimney cap | Day off | Day off | H7 broken glazing variants and M_Master_Glass + Review 7 | Buffer: catch up on anything late from Weeks 3 to 7 | Buffer
C04 Pipe and cable bracket, wall hook | 10 to 30
C05 Handrail: straight, post, bend, end cap | 100, 150, 200 | [5 empty] | 2026-11-30: Week 8 · Props and debris
C06 Gutter run and bracket | 200, 400 | [5 empty] | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13
Kit D · Ground | Size (cm) | Blockout | Model | UVs | Material | In UE5 | P01 plywood, P02 planks, P03 offcuts | P04 bricks and P05 rubble piles | Day off | Day off | P06 pipes, P07 cable spline, P08 fallen gutter, P09 broken frame | P10 glass shards, P11 dead branches, P12 corrugated sheet, P15 litter, P16 paper | P17 junction box, P18 lamp bracket, then P3 props if time + Review 8
D01 Ground tile, setts under mud | 400 x 400 | [5 empty] | 2026-12-07: Week 9 · Foliage
D02 Kerb / wall-base strip | 400 long | [5 empty] | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20
D03 Drain grate and channel | 100 x 30 | [5 empty] | Model leaves | F01 ivy cards and vine splines | Day off | Day off | F02 moss clumps, F03 grass and weeds, F05 dead leaves | F04 buddleia, F06 brambles, F07 saplings | F08 background trees and the H5 far opening mass + Review 9
D04 Rubble edge strip (ground meets wall) | 400 long
D05 Broken ground patch (exposed setts) | 200 x 200 | [5 empty] | 2026-12-14: Week 10 · Decals and vertex paint
D06 Puddle insert (shallow depression) | 150 x 100 | [5 empty] | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27
D07 Wall-base dirt pile | 200 long | [5 empty] | Build decals X01 to X04 and M_Master_Decal | Build decals X05 to X08 | Day off | Day off | Buffer (Christmas) | Vertex paint both facades | Place decals + Review 10
Hero features | Size (cm) | Blockout | Highpoly | Lowpoly | Texture | In UE5
Week 11 · Set dressing
H1 Two-tier skybridge | 500 span x 340 h x 250 d | [5 empty] | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-01 | 2027-01-02 | 2027-01-03
H2 Chimney stack and red end building | 180 x 2800 h x 180 | [5 empty] | Ground dressing | Place P1 props in Camera 1 for composition | Day off | Day off | Buffer (New Year's Day) | Foliage placement + Review 11 | Buffer
H3 Basement light well with green handrail | 120 x 200 drop x 380
H4 Cascading ivy and wall growth | [6 empty] | 2026-12-28: Week 12 · Dressing for alternate angles
H5 Overgrown far opening | [6 empty] | 2027-01-04 | 2027-01-05 | 2027-01-06 | 2027-01-07 | 2027-01-08 | 2027-01-09 | 2027-01-10
H6 Rusted arched loading doors | 240 x 320 | [5 empty] | Dress the alternate cameras with P2 props, glass, litter, paper | Puddles and wetness | Day off | Day off | Buffer | Full walkthrough + Review 12 | Buffer
H7 Broken industrial glazing | 140 x 220
Props | Size (cm) | Blockout | Highpoly | Lowpoly | Texture | In UE5 | 2027-01-04: Week 13 · Lighting and atmosphere
[7 empty] | 2027-01-11 | 2027-01-12 | 2027-01-13 | 2027-01-14 | 2027-01-15 | 2027-01-16 | 2027-01-17
P01 Plywood sheet, warped and delaminating | 122 x 244 | [5 empty] | Overcast sky | Height fog and volumetrics | Day off | Day off | Post process | Light the alternate cameras | Review 13
P02 Timber planks, 4 variants | 15 x 240
P03 Broken timber offcuts, 6 variants | 10 to 60 | [5 empty] | 2027-01-11: Week 14 · Polish and optimization
P04 Loose bricks and half bricks, 6 variants | 23 x 11 | [5 empty] | 2027-01-18 | 2027-01-19 | 2027-01-20 | 2027-01-21 | 2027-01-22 | 2027-01-23 | 2027-01-24
P05 Rubble pile cluster, 3 variants | 100 to 200 | [5 empty] | Apply critique notes | Material polish | Day off | Day off | Optimization | Audit texel density, wireframes, naming | Final polish in Camera 1 + Review 14
P06 Rusted pipe lengths, 3 variants | 100 to 300
P07 Hanging and loose cables, spline | any | [5 empty] | 2027-01-18: Week 15 · Final renders
P08 Fallen gutter section | 200 | [5 empty] | 2027-01-25 | 2027-01-26 | 2027-01-27 | 2027-01-28 | 2027-01-29 | 2027-01-30 | 2027-01-31
P09 Broken window frame on ground | 140 x 220 | [5 empty] | Beauty renders at 4K with Movie Render Queue | Breakdown renders | Day off | Day off | Marmoset turntables for H1, H2, H6 and a prop sheet | Edit the 30 to 45 second flythrough in Blender's Video Sequencer | Lay out and publish the ArtStation post with breakdown text
P10 Glass shards scatter, 8 pieces | 5 to 20
P11 Dead branches, 5 variants | 50 to 200
P12 Corrugated sheet, bent | 80 x 200
P13 Rusted barrel or drum, on its side | 60 diameter
P14 Crate, broken | 60 x 60
P15 Plastic litter: bags, bottles, cans | 5 to 40
P16 Paper and cardboard scraps | 10 to 50
P17 Wall-mounted junction box | 30 x 40
P18 Old wall lamp bracket | 40
P19 Fallen roof slates | 25 x 50
P20 Pallet, rotten | 120 x 100
P21 Wire mesh panel, crumpled | 100 x 200
P22 Hose or flex pipe, spline | any
Vegetation | Size (cm) | Model | Atlas | Material | Wind | Placed
F01 Ivy cards and vine splines
F02 Moss clumps, 3 sizes
F03 Grass and weed tufts, 6 variants
F04 Buddleia bush (grows from walls)
F05 Dead leaves scatter
F06 Brambles
F07 Small birch and sycamore saplings
F08 Background trees (far opening)
F09 Roof-edge weeds for the chimney building
F10 Ferns in damp corners
Tile-Textures | Size (cm) | Source | Customize | Masks | Bake | In UE5
M01 Brick, sooty dark (Victorian, recessed mortar) | 200 x 200 tile
M02 Brick, grey limewash peeling to red brick | 200 x 200 tile
M03 Brick, red clean (background) | 200 x 200 tile
M04 Brick infill, mismatched | 200 x 200 tile
M05 Ground setts under mud | 200 x 200 tile
M06 Mud and dirt with organic debris | 200 x 200 tile
M07 Concrete, weathered | 200 x 200 tile
M08 Moss and algae | 100 x 100 tile
M09 Timber, painted and peeling (red, green) | 200 x 200 tile
M10 Rusted painted metal | 100 x 100 tile
Trim sheets | Size (cm) | Model | Bake | Texture | Material | In UE5
T01 Stone trim sheet | 2048 px, 10.24 px/cm
T02 Metal trim sheet | 2048 px, 10.24 px/cm
T03 Timber trim sheet | 2048 px, 10.24 px/cm
Decals | Size (cm) | Source | Bake | Texture | Material | Placed
X01 Water leaks and streaks under sills and pipes
X02 Soot and grime gradients up from the ground
X03 Moss and algae patches
X04 Brick damage, spalling and cracks
X05 Peeling paint edges (right wall)
X06 Rust bleed from metal fixings
X07 Puddle and wet-ground patches
X08 Oil stains and mud tracks
X09 Old painted signage, faded
Done
In Progress
Not Started
Change a stage cell's fill colour to update its status.
Note on I4: Build a reference board (a Blender reference scene or any image board): the photo plus 40+ supporting shots (northern English mills, Victorian brick, steel windows, skybridges, ivy on brick). Done when: sorted by scene zone.
Note on J4: Paint over the reference: circle every repeating element (kit) and every one-off (hero); draft kit IDs. Done when: annotated paintover saved.
Note on M4: Camera match in Blender: photo as camera background, align the vanishing lines, set focal length; block primitive volumes at the measured sizes. Done when: overlay lines up with the photo.
Note on N4: Lock metrics, naming and folders; set up the UE5 project and source control (Git LFS or Perforce). Done when: metrics sheet and empty project committed.
Note on O4: Lighting and mood paintover (overcast, cool, wet); Review 1. Done when: target image saved next to the reference.
Note on I8: Greybox ground and both building masses in UE5 at scale; place a 180 cm mannequin. Done when: walkable alley.
Note on J8: Greybox the left facade with placeholder A01 to A09 at final dimensions. Done when: left wall reads like the photo.
Note on M8: Greybox the right facade with B01 to B09, including the ledge and light well. Done when: right wall reads like the photo.
Note on N8: Greybox skybridge, chimney, end building and loading door; set Camera 1 (reference match) and 3 alternate cameras. Done when: full silhouette matches.
Note on O8: Blockout lighting (sun, sky, fog), walkthrough, Review 2; lock the greybox. Done when: side-by-side greybox vs reference.
Note on I12: Source CC0 base materials (ambientCG, Poly Haven, Blendkit free) for sooty brick, painted brick, setts, mud, concrete, moss, timber and rusted metal; rescale each to the 200 cm tile metric. Done when: 10 base sets in a Blender material library.
Note on J12: Build custom mask node groups in Blender: edge wear (Bevel and AO nodes into a noise-broken threshold) and leak streaks (object-space vertical gradient times stretched noise, starting under sills and ledges). Done when: both masks drive a test wall module.
Note on M12: Brick sets M01 to M04: soot, limewash peel and infill variations layered with the mask groups; bake to 2K tiling sets. Done when: brick sets tile cleanly at 200 cm.
Note on N12: M05 to M10 (setts, mud, concrete, moss, timber, rusted metal): adjust and bake to 2K; bake edge-wear and leak masks for the kit test pieces. Done when: all 10 materials exported.
Note on O12: Build M_Master_Kit in UE5: vertex height blend, world-aligned moss, a world-space leak streak and a baked edge-wear input; Review 3. Done when: painting moss, grime and wet works.
Note on I16: Model T01 stone and T02 metal trim strips in Blender; bake to 2048 sheets in Marmoset. Done when: 2048 sheets with normal, AO, height.
Note on J16: T03 timber trim sheet; M_Master_Trim; set up a texel density checker. Done when: all three sheets in engine.
Note on M16: Model A01, A02, A06, A09 with bevels and UVs. Done when: snap test passes on the 25 cm grid.
Note on N16: Model A03 blind arch with infill, A05 door surround, A07 string course, A08 parapet. Done when: in engine with materials.
Note on O16: Model A04 window; replace the left greybox with the kit; Review 4. Done when: left wall fully kit-built.
Note on I20: Model B01, B07, B08, B09. Done when: snap test passes.
Note on J20: Model B02 window bay and the three B03 steel window variants. Done when: bays swap variants cleanly.
Note on M20: Model B04 door bay, B05 ledge, B06 light well. Done when: right wall fully kit-built.
Note on N20: Model Family C: beams, drainpipes, hopper head, brackets, handrail, gutters. Done when: pipes run full height with no gaps.
Note on O20: Model Family D ground pieces; replace all remaining greybox; Review 5 with a kit-only screenshot. Done when: the alley is 100% kit.
Note on I24: Plan the skybridge from reference; model the base mesh (frame, cladding boards, windows, girder deck). Done when: matches greybox volume.
Note on J24: Sculpt in Blender: warped and broken boards, rot, sagging, splintered window frames. Done when: high poly reads at Camera 1 distance.
Note on M24: Retopo the low poly, UV into two 4K sets. Done when: under 40,000 tris, clean UVs.
Note on N24: Bake in Marmoset; start the Marmoset texture project: peeling red and green paint, rot, rust on girders. Done when: base materials and masks in.
Note on O24: Finish texturing, import, place; Review 6 against the reference. Done when: skybridge final in Camera 1.
Note on I28: Model the chimney and red end building; sculpt the corbelled cap. Done when: silhouette locked.
Note on J28: Texture the chimney cap; model and texture H6 rusted loading doors. Done when: both final in engine.
Note on M28: H7 broken glazing variants and M_Master_Glass; assemble H3 light well vignette; Review 7. Done when: all heroes in scene.
Note on I32: P01 plywood, P02 planks, P03 offcuts. Done when: textured and placed in a prop gallery level.
Note on J32: P04 bricks and P05 rubble piles (sculpt, bake, atlas). Done when: 3 rubble clusters ready.
Note on M32: P06 pipes, P07 cable spline, P08 fallen gutter, P09 broken frame. Done when: cable spline usable in level.
Note on N32: P10 glass shards, P11 dead branches, P12 corrugated sheet, P15 litter, P16 paper. Done when: all P1 and P2 small props done.
Note on O32: P17 junction box, P18 lamp bracket, then P3 props if time; Review 8 with a prop sheet. Done when: prop gallery screenshot.
Note on I36: Model leaves (ivy, buddleia, grass, weeds) in Blender and bake a foliage atlas in Marmoset. Done when: atlas with opacity, normal, translucency.
Note on J36: F01 ivy cards and vine splines; place H4 ivy down the left wall and drainpipe. Done when: ivy breaks the parapet line like the photo.
Note on M36: F02 moss clumps, F03 grass and weeds, F05 dead leaves. Done when: paintable with the foliage tool.
Note on N36: F04 buddleia, F06 brambles, F07 saplings. Done when: all with wind.
Note on O36: F08 background trees and the H5 far opening mass; Review 9. Done when: far end reads bright and green.
Note on I40: Build decals X01 to X04 and M_Master_Decal. Done when: decals project cleanly on brick.
Note on J40: Build decals X05 to X08. Done when: full decal library in engine.
Note on N40: Vertex paint both facades: moss where water sits, grime rising from the ground, wet under leaks. Done when: no visible tiling in Camera 1.
Note on O40: Place decals: leaks under sills, rust bleed under fixings, soot gradients, peeling edges. Review 10: Camera 1 vs the photo; list fixes. Done when: every sill and pipe has a story and the fix list is written.
Note on I44: Ground dressing: rubble edges along wall bases, debris following drainage and foot traffic. Done when: ground matches photo density.
Note on J44: Place P1 props in Camera 1 for composition (plywood, planks, branches, cables). Done when: leading lines point to the far opening.
Note on N44: Foliage placement: weeds in cracks, moss on ledges and steps, buddleia in mortar; Review 11. Done when: foreground to background reads clearly.
Note on I48: Dress the alternate cameras with P2 props, glass, litter, paper. Done when: no empty corners in any camera.
Note on J48: Puddles and wetness: X07 decals, D06 inserts, wet roughness on the ground. Done when: puddles reflect the sky.
Note on N48: Full walkthrough: fix floating objects, seams, repeated props; Review 12. Done when: clean walkthrough capture.
Note on I52: Overcast sky (HDRI or Sky Atmosphere), soft directional, skylight, Lumen settings; lock exposure. Done when: flat, cool base matches the photo.
Note on J52: Height fog and volumetrics; a soft light shaft at the far opening; bounce and fill lights. Done when: depth reads in three layers.
Note on M52: Post process: colour grade toward the photo, light vignette, grain; tune reflections on glass and puddles. Done when: Camera 1 sits next to the photo convincingly.
Note on N52: Light the alternate cameras. Done when: each has a clear focal point.
Note on O52: Review 13: share lit renders with peers or a mentor for critique. Done when: critique notes collected.
Note on I56: Apply critique notes. Done when: every note fixed or consciously skipped.
Note on J56: Material polish: tiling breakup, roughness ranges, greyscale value check. Done when: scene reads in greyscale.
Note on M56: Optimization: Nanite and LODs, texture streaming, collision, profile with stat unit and GPU visualizer. Done when: stable frame rate in a walkthrough.
Note on N56: Audit texel density, wireframes, naming; build a kit breakdown level with every module laid out. Done when: breakdown level ready to shoot.
Note on O56: Final polish in Camera 1; lock the scene; Review 14. Done when: scene locked.
Note on I60: Beauty renders at 4K with Movie Render Queue: Camera 1 plus 4 to 6 angles. Done when: all beauty shots exported.
Note on J60: Breakdown renders: kit sheet, wireframe, clay, lighting only, material spheres, trim sheets. Done when: breakdown set exported.
Note on M60: Marmoset turntables for H1, H2, H6 and a prop sheet; render the flythrough sequence. Done when: all renders on disk.
Note on N60: Edit the 30 to 45 second flythrough in Blender's Video Sequencer; make the reference vs final side-by-side. Done when: video exported.
Note on O60: Lay out and publish the ArtStation post with breakdown text; update portfolio. Done when: project is live.

## Measurements
Reference breakdown · 1:1 scale
Estimates from human-scale anchors (100 cm handrail, 18 cm risers, 210-260 cm doors, Victorian brick coursing). Confirm by camera-matching the photo in Blender.
Element | Width (cm) | Height (cm) | Depth (cm) | Notes
Alley, wall to wall | 500 |  | 4000 visible length | about 400 clear walkway beside the light well
Left mill height |  | 2000 |  | 5 storeys at 400 floor to floor, plus parapet
Right building height |  | 1900 |  | 5 storeys at about 380 floor to floor
Brick (Victorian imperial) | 23 | 7.6 | 11 | 1 cm joints, so 8.6 cm per course, about 12 courses per metre
Left pilaster | 60 | full height | 25 projection | every 400 along the wall
Left blind arch recess | 200 | 550 | 25 recess | round head, bricked-up infill
Left arched loading door | 240 | 320 | 40 reveal | rusted sheet doors
Right window opening | 140 | 220 | 30 reveal | steel frame, panes about 25 x 35
Right window bay spacing | 300 | 380 |  | 160 of brick pier between openings
Stone sill | 160 | 15 | 20 | 5 projection, drip groove
Stone lintel | 170 | 30 | 30 | flush or 2 projection
Right mossy ledge / plinth | runs wall | 50 | 60 | top surface takes world-aligned moss
Basement light well | 120 | 200 drop | 380 | 11 risers at 18, treads 28
Handrail | 4.2 diameter | 100 |  | posts every 150, painted green
Skybridge, enclosed tier | 500 span | 300 | 250 | underside at about 600 above ground
Skybridge, girder deck | 500 span | 40 | 250 | steel I-beams about 30 deep, sits under the enclosed tier
Chimney stack | 180 | 2800 to top | 180 | top at about 28 m, corbelled cap
Cast-iron drainpipe | 10 diameter | full height |  | hopper head 30 x 30, brackets every 180
Plywood sheet | 122 | 1.8 | 244 | prop
Timber plank | 15 | 5 | 240 | prop
Ground setts (cobbles) | 10 |  | 20 | mostly buried under mud and debris
Metrics to hold
Grid snap 25 cm; modules on 100, 200 and 400 cm widths.
Floor to floor 400 (left) and 380 (right); pivots at bottom-left-back of each module.
Texel density 10.24 px/cm (1024 px/m) for surfaces within 5 m of camera; 5.12 px/cm for upper floors and background.
Brick tiling texture covers 200 x 200 cm with 24 courses (8.33 cm each, a small cheat on the real 8.6) so coursing lines up at every 100 cm module edge.